## Slide 1
First Quarter FY26 Monthly Business Performance Review
April 15th, 2026

## Slide 2
EBS Updates

## Slide 3
EBS Updates
EBS Project Portfolio | March 2026 | Monthly Business Review
Portfolio Status
On Track
22
Delayed
2
On Hold
3
Completed
3
30 Projects
Total Active Portfolio | Apr 2026
📎 Full Projects Roadmap & Tracker
New This Month
Payroll — ERP Integration
Dealer Orders Prepayments
PO Workflow & Mobile Approvals
Van Sales Credit Operations
Asset Management — Vendor evaluation and solution finalization
Footfall analysis Solution — Project Kickoff
March Highlights
Sales Forecast — Delivered and closed
Showroom Rollout — Sabah Al Salem Showroom
International Barcodes — Rollout completed
Service Contracts — UAT underway, 65% complete
Stock Take Enhancements — 85% done. Sign-off pending
Ecommerce Soft Launch — ERP Integration development Completed
IMEI Tracking — 95% complete, final execution stage
Power BI Reports — 6 reports delivered
Risks & Issues
Ecommerce Soft Launch delayed — UAT instance readiness and dev completion by SF partner
Service Tech App delayed — was Feb, now Jun 2026
Stock Take — Sign-off blocked. Operations to resolve physical vs system expiry data mismatch.
Talabat Integration — On hold. Re-engage with commercial team to align priorities.
Post-demo scope changes on 2 retail apps — adding delivery risk to May timelines
Payroll Integration — partner resource alignment pending
April 2026 Focus
Ecommerce Soft Launch — UAT completion target 25 April (subject to SF partner & Merchandising readiness)
Dealer Prepayments — Go-live 30 April 2026
PO Workflow — Demo 24 April, go-live 1 May 2026
Service Tech App 15 April— Development handover to EBS, testing begins
People Engagement Platform — Vendor demo scheduled
Extended Warranty & Installation — CR ongoing, go-live May 2026
DocuSign — Trial evaluation, license confirmation this month
Van Sales Credit Operations — Go-live 20 April
Service Contracts — UAT sign-off and go-live target April
Sophos MDR — Go-live pending executive approval
Decisions Required
Operations — Resolve expiry data mismatch issues and signoff to kickstart integration project mismatch by 25 April.
Finance — Upload approved PO budgets in live by 22 April to enable PO workflow go-live on 1 May.
Executive — Approve Digital Price Tags vendor selection to proceed with integration.
Commercial — Re-engage Talabat & ERP partner. Integration on hold until actioned.
Marketing — Confirm revised Ecommerce go-live date.
Finance — Payment due to close Sophos MDR project